## DayBook
LOGBOOK |  |  |  | Jarryd van Zanten - Y9441843 - TM470
DATE | TIME | Log # | Hours spent | WORK | Problems | Comments
2016-02-17 | 19:00 | 1 | 2 | Following reading of module materials, set up project gantt plan, project log and git repositories | Difficult to gauge which software to use for planning and how in depth the plan should be. Trying to work out a nice way of keeping a project log but still utilise the gantt functionality. Settled on this spreadsheet. | Decided to separate the project documents and development files, so that the development can be more easily scrapped and restarted if things go wrong.
2016-02-17 | 20:00 | 2 | 1 | Writing up project goals, resources, |  | Initially hand writing ideas for quicker thought process. May need to take photos for assessment?
2016-02-19 | 22:00 | 3 | 3 | Reading of M258 module materials, fleshing out of planner and thinking of initial structure for TMA. Setting up planner for recording risks and issues - can be used to track bugs, as well as requirements and RFCs. Posted on BGG, asking for advice on similar software. Reading on RAID concepts | Need to write thoughts down more, so that I can order my thinking more. | Considering using Evernote or similar for a logbook so that I can include pictures of notes and links/bookmarks, etc. - would also make reading on mobile easier than spreadsheet